## Burndown Chart
Burn Down Chart
|  | Pts Done | Pts Remaining | Done For Week |  |  | Could | Won't
| Week |  |  |  | Must | Should
| 0 |  | 35 | N/A
Jan 13-Jan 19 | 1 | 1 | 34 | 1 | 0 | 1 | 0 | 0
Jan 20-Jan 26 | 2 | 5 | 29 | 5 | 4 | 1 | 0 | 0
Jan 27-Feb 2 | 3 | 1 | 28 | 1 | 1 | 0 | 0 | 0
Feb 3-Feb 9 | 4 | 2 | 26 | 2 | 0 | 2 | 0 | 0
Feb 10-Feb 16 | 5 | 3 | 23 | 3 | 2 | 1 | 0 | 0
Feb 17-Feb 23 | 6 | 4 | 19 | 4 | 2 | 2 | 0 | 0
Feb 24-Mar 1 | 7 | 5 | 14 | 5 | 1 | 4 | 0 | 0
Mar 2-Mar 8 | 8 | 2 | 12 | 2 | 0 | 1 | 1 | 0
Mar 9-Mar 15 | Break | 0 | 12 | 0 | 0 | 0 | 0 | 0
Mar 16-Mar 22 | 10 | 2 | 10 | 2 | 1 | 1 | 0 | 0
Mar 23-Mar 29 | 11 | 1 | 9 | 1 | 1 | 0 | 0 | 0
Mar 30-Apr 5 | 12 | 1 | 8 | 1 | 0 | 0 | 1 | 0
Apr 6-Apr 12 | 13 | 1 | 7 | 1 | 1 | 0 | 0 | 0
Apr 13-Apr 19 | 14 | 1 | 6 | 1 | 0 | 1 | 0 | 0
Apr 20-Apr 26 | 15 | 2 | 4 | 2 | 0 | 1 | 1 | 0

## Sheet1
Burn Down Chart
|  | Pts Done | Pts Remaining | Done For Week |  |  | Could | Won't
| Week |  |  |  | Must | Should
| 0 |  | 35 | N/A
Jan 13-Jan 19 | 1 | 1 | 34 | 1 | 0 | 1 | 0 | 0 | FS1 - should
Jan 20-Jan 26 | 2 | 5 | 29 | 5 | 4 | 1 | 0 | 0 | FS11 - must, FS14 - shoulld, FS31 Must, FS33 Must, FS30 must
Jan 27-Feb 2 | 3 | 1 | 28 | 1 | 1 | 0 | 0 | 0 | NM1 - Must
Feb 3-Feb 9 | 4 | 2 | 26 | 2 | 0 | 2 | 0 | 0 | FS-2 Should, FS-3-Should,
Feb 10-Feb 16 | 5 | 3 | 23 | 3 | 2 | 1 | 0 | 0 | FS-5 Should, FM-3 Must, FM-1 Must
Feb 17-Feb 23 | 6 | 4 | 19 | 4 | 2 | 2 | 0 | 0 | FS-4 Should … FS27 Must FS9 Should, FS15 Must
Feb 24-Mar 1 | 7 | 5 | 14 | 5 | 1 | 4 | 0 | 0 | FS-6 Should, FS32 Must,FS13 Should FS12 Should, FS18 Should
Mar 2-Mar 8 | 8 | 2 | 12 | 2 | 0 | 1 | 1 | 0 | FS-23 should, FS-24 could
Mar 9-Mar 15 | Break | 0 | 12 | 0 | 0 | 0 | 0 | 0 | none
Mar 16-Mar 22 | 10 | 2 | 10 | 2 | 1 | 1 | 0 | 0 | FS-8 should, FS-17 must
Mar 23-Mar 29 | 11 | 1 | 9 | 1 | 1 | 0 | 0 | 0 | FS-16 must
Mar 30-Apr 5 | 12 | 1 | 8 | 1 | 0 | 0 | 1 | 0 | FS-19 could
Apr 6-Apr 12 | 13 | 1 | 7 | 1 | 1 | 0 | 0 | 0 | FS-20 must
Apr 13-Apr 19 | 14 | 1 | 6 | 1 | 0 | 1 | 0 | 0 | FS-21 should
Apr 20-Apr 26 | 15 | 2 | 4 | 2 | 0 | 1 | 1 | 0 | FS-22 could, FS-29 should
Completed | ID | Type |  | Total | 13 | 16 | 6 |  |  |  |  | fs10 | could | messaging
| FS1 | Should | [6 empty] | FS8 | should | timeline | fs25 | could | have admin view edits
| NM1 | Must | [6 empty] | FS16 | must | invest in capstone | fs28 | could | messaging w/ sponsor
| FS11 | Must | [6 empty] | FS17 | must | prof can create a capstone | fs29 | should | marketing user review requests
| FS14 | Should | [6 empty] | FS19 | could | share social media | fs26 | should | sponsor can see more
[9 empty] | FS20 | Must | approve sponsorship | fs22 | could | view past sponsor requests
[9 empty] | FS21 | Should | deny sponsorship
[9 empty] | FS23 | should | edit capstone page
[9 empty] | FS24 | could | edit capstone page
[9 empty] | FS30 | must | allow an admin to change user permissions
Missing
[9 empty] | fs10 | could | messaging
[9 empty] | fs25 | could | have admin view edits
[9 empty] | fs28 | could | messaging w/ sponsor
[9 empty] | fs26 | should | sponsor can see more